## Sheet1
Kenai River Baseline Water Quality Monitoring Program Tasks
Sourced from the Quality Assurance Project Plan 1/27/2023
Frequency | Month | Responsible Party | Responsible Person | Task | Page
Annual | February | Technical Advisory Committee | Committee Members | Review annual results from previous year | 9
Annual | March | Kenai Watershed Forum | Project Manager / Project QA Officer | Uplift previous year's data that passed QA review to the EPA Water Quality Exchange | 38, 39
Annual | March | Kenai Watershed Forum | Project Manager / Project QA Officer | Review previous year's data for five-year trends in the context of regulatory values | 39
Annual | December | Kenai Watershed Forum | Project Manager / Project QA Officer | Produce a QA summary report and submit to the Project Manager, ADEC Project Manager, and ADEC QA Officer. | 31, 41
Biannual | March | Technical Advisory Committee | Committee Members | Review QAPP and overall project design | 41
Biannual | March/May | Kenai Watershed Forum | Project Manager | Confirm sampling teams | 28
Biannual | April/May | Kenai Watershed Forum | Project Manager | Transfer field samples to laboratories | 29
Biannual | July/August | Kenai Watershed Forum | Project Manager | Receive data from laboratories | 39
Biannual | March/May | Kenai Watershed Forum | Project Manager / Project QA Officer | Confirm laboratory schedules and capabilities
Five years | - | Kenai Watershed Forum | Project Manager / Project QA Officer | Produce comprehensive data review, contingent on funding | 42