## project_information
Project Name | Kenai River Baseline Water Quality Monitoring
Waterbody Name(s) | Kenai River, No-Name Creek, Beaver Creek, Slikok Creek, Soldotna Creek, Moose River, Funny River, Killey River, Russian River, Juneau Creek
Assessment Unit ID(s) | UNK
Project Manager | Benjamin Meyer
Data Conducting Organization | Kenai Watershed Forum
Data Collection Dates | 5/11/2021, 7/27/2021

## data_evaluation_summary
Review Step | Review Task | Responsible person | Name | Date Completed
Pre-Database | Raw data review during field season | KWF Project Manager | Benjamin Meyer | 2021-09-01
| Complete project and raw data review post field season | KWF Project Manager | Benjamin Meyer
Database Prep | Import configuration file review | KWF Project Manager
Database Import | Courtesy EPA WQX and data export review | ADEC Staff
| Corrected AWQMS and data export review* | KWF Project Manager
| QA Review | KWF Project Manager
| Final review | KWF Project Manager

## data_evaluation_checklist
seq | data submission ID | stage | sub_category | task | manual response | criteria 1 | criteria value 1 | notes | dev_notes | dev_sequence
1 | kenai_baseline_2021 | pre_database | analytical_lab | Were the appropriate analytical methods used for all parameters? |  |  |  | 2021 sampling plan was executed as outlined in the approved 2020 QAPP
2 | kenai_baseline_2021 | pre_database | overall_success | Were there any deviations from the sampling plan? | N |  |  | 2021 sampling plan was executed as outlined in the approved 2020 QAPP | sampling plan can be execute correctly, and if CoC is incorrect, analysis can still be carried out incorrectly
3 | kenai_baseline_2021 | pre_database | overall_success | Were field duplicates, blanks, and/or other QC samples collected as planned? |  |  |  |  | make as one of the first questions. Evaluate outside of this sheet, results context-specific outside of QAPP values | early
4 | kenai_baseline_2021 | pre_database | analytical_lab | Do the laboratory reports provide results for all sites and parameters? | Y
5 | kenai_baseline_2021 | pre_database | analytical_lab | Is a copy of the COC included with the laboratory reports? | Y
6 | kenai_baseline_2021 | pre_database | analytical_lab | Do the laboratory reports match the COC and requested methods throughout? |  |  |  | Site names are sometimes misspelled between CoC and lab rsults
7 | kenai_baseline_2021 | pre_database | analytical_lab | Are the number of samples on the laboratory reports the same as on the COC? |  |  |  | manual check?
8 | kenai_baseline_2021 | pre_database | analytical_lab | Was all supporting info provided in the laboratory report, such as reporting limits for all analyses and definitions?
9 | kenai_baseline_2021 | pre_database | overall_success | Are site names, dates, and times correct and as expected? | Y |  |  | Despite providing pre-printed labels on all sample bottles, there were numerous mis-spellings and inconsistencies in the electronic data delivery (EDD) files received from the laboratories. The site name issues were corrected in post-season data review. For future years, we may consider providing a spreadsheet to the labs with all site names to encourage using these electronic entries directly.
10 | kenai_baseline_2021 | pre_database | insitu_instruments | Were there any issues with instrument calibration? | [5 empty] | early
11 | kenai_baseline_2021 | pre_database | insitu_instruments | Did the instrument perform as expected? | [5 empty] | early
12 | kenai_baseline_2021 | pre_database | insitu_instruments | Was instrument calibration performed according to the QAPP and instrument recommendations? | [5 empty] | early
13 | kenai_baseline_2021 | pre_database | insitu_instruments | Was instrument verification during the field season performed according to the QAPP and instrument recommendations?
14 | kenai_baseline_2021 | pre_database | insitu_instruments | Were instrument calibration verification logs or records kept?
15 | kenai_baseline_2021 | pre_database | insitu_instruments | Do the instrument data files site IDs, time stamps and file names match?
16 | kenai_baseline_2021 | pre_database | insitu_instruments | Is any insitu field data rejected and why?
17 | kenai_baseline_2021 | pre_database | analytical_lab | Were preservation, hold time and temperature requirements met?
18 | kenai_baseline_2021 | pre_database | analytical_lab | Are dissolved metal quantities less than total metals quantities?
19 | kenai_baseline_2021 | pre_database | overall_success | Are the duplicate sample(s) RPD within range described in QAPP? |  | rpd | misc | Include parameters, site names, dates, results and RPD values. | Put question later; need to first evaluate if samples CAN be used to calculate RPD. May need to a create separate table ( I think I have one already in progress!) to evaluate against many different numbers | late
20 | kenai_baseline_2021 | pre_database | analytical_lab | Were there any laboratory discrepancies, errors, data qualifiers, or QC failures (review laboratory duplicates, matrix spikes and blanks)? |  |  |  |  | report qualifiers for each obervation, AND see lab notes
21 | kenai_baseline_2021 | pre_database | analytical_lab | Is any laboratory data rejected and why?
22 | kenai_baseline_2021 | pre_database | overall_success | During the field season, review raw data files (EDDs, instrument records) as they are received. Document changes and corrections to methods as needed.
23 | kenai_baseline_2021 | pre_database | overall_success | Is the dataset complete and did you receive the expected number of results? |  |  |  | see "completeness measures" | Make this one of the last questions. Wait until after sensityovity and RPD filters have been applied
24 | kenai_baseline_2021 | pre_database | overall_success | Was the data collected representative of environmental conditions? | Y |  |  | Study design is intended to annually create two single-day snapshots across a wide geographical area of the Kenai River watershed. Answer can be qualitatively determined after seeing what data passes QA/QC requirements
25 | kenai_baseline_2021 | pre_database | overall_success | Does project meet Completeness Measure A criteria? |  | complete_a | 85% | Completeness Measure A = The primary number of samples collected divided by the useable number of samples submitted to EPA with a goal of 85% completeness |  | late
26 | kenai_baseline_2021 | pre_database | overall_success | Does project meet Completeness Measure B criteria? |  | complete_b | 60% | Completeness Measure B = The planned number of samples divided by the useable samples (submitted to EPA) with a goal of 60%. Include parameter information, number of expected samples, number of collected samples and overall percent completeness. |  | late
27 | kenai_baseline_2021 | pre_database | analytical_lab | Was the QA Officer consulted for any data concerns? |  |  |  |  | general answer will always be yes, set QA officer report
28 | kenai_baseline_2021 | database_prep | database | Are the correct monitoring locations associated with the project?
29 | kenai_baseline_2021 | database_prep | database | Are the QAPP and other supporting documents attached?
30 | kenai_baseline_2021 | database_prep | database | Is all metadata correct?
31 | kenai_baseline_2021 | database_prep | database | Is the organization ID correct?
32 | kenai_baseline_2021 | database_prep | database | Are the time zones consistent and correct (AKDT in summer)?
33 | kenai_baseline_2021 | database_prep | database | Are all media types included? Media types appropriate to Characteristic?
| kenai_baseline_2021 | database_prep | database | Check Sample Collection, Preparation and Preservation Methods, Thermal Preservative, Equipment ID, Activity Media. Is supporting information included and correct?
| kenai_baseline_2021 | database_prep | database | Are all expected activity types present and are QC samples correctly identified?
| kenai_baseline_2021 | database_prep | database | Is the Activity media subdivision filled in (if relevant)?
| kenai_baseline_2021 | database_prep | database | For Water activity media, is the relative depth filled in?
| kenai_baseline_2021 | database_prep | database | Is the number of results for each Characteristic correct?
| kenai_baseline_2021 | database_prep | database | Do the range of result values make sense, are units correct?
| kenai_baseline_2021 | database_prep | database | Are detection limits and laboratory qualifiers included for analytical results?
are units consistent for each parameter
are trip blanks below detection levels
Note on J1: Author: KWF is in the process of developing a script that addresses each of these rows individually, for each annual data submission
Note on K1: Author: sequence of logical evaluation